## Calendar For Festive and other
This sheet is to be maintained 3 months prior

## Event Overview
Event Name | Event Date | Day | Age Group | Category | Indoor/Outdoor | Seating Arrangement | Location | Kid Friendly | Pet Friendly
Garba Workshop | 26th July 2025 | Saturday | No limit | Workshop | Outdoor | Yes | Encore-Himalaya Mall | Yes | No
Eco Friendly Ganpati Making | 25th Aug 2025 | Sunday | No limit | workshop | Indoor | Yes | Mr potter art cafe | Yes | No
Pre-Navratri+ Garba Workshop | 13 sept 2025 | Sunday | 13+ | Party | Outdoor | Yes | Not Finalized | No | No
Fake Sangeet | 2025-10-11 | Saturday | 13+ | Party | Outdoor | Yes | Not Finalized | No | No
Fitnes Event | oct |  |  |  | Outdoor
Standup | oct |  |  |  | Indoor
Cruise event + Prom Night | oct |  |  |  | Outdoor | yes
New year Party | 2025-12-31 | Wednesday | 18+ | Party | Outdoor | Yes | Udaipur | No
Starry Movie Night | 22nd Nov | Sat
Pickle Ball & Cricket | 29th Nov | Sat
Games Get together
Exclusive teacher's event/party | December 6th | Saturday | No limit | Fun gathering | Indoor | Yes | Will find out | - | -
Mystery meetup
Car meetup
Panipuri event | January
Housie event | November end
Cozy movie night | February
Freshers Party - CBSE
Freshers Party - GSEB
K-Pop Dance workshop |  |  | No limit |  | Indoor
K-Pop event |  |  | No limit |  | Indoor
Cafe Hop |  |  | 13+ |  | Indoor
Candlelight Concert at a Vav
New Year Event | 31st Dec 2025 | Wed | above 18 | Party | Outdoor | yes | Udaipur | Yes | No

## Pre-Event Task Tracker
Event | Task Phase | Order | Task | Assigned To | Deadline | Status | Notes | Remarks(Inclusion/Exclusion)
Garba Workshop | Planning & Pre-Production | 1 | Concept Finalization | Mansi | 19 June to 25 June | Completed
|  | 2 | Budget Approval | Mansi | 19 June to 25 June | Completed
|  | 3 | Event Date Finalization | Mansi | 19 June to 25 June | Completed
|  | 4 | Venue Finalization | Mansi | 19 June to 25 June | Completed
|  | 5 | Permission & Licenses (if required) | Mansi | 19 June to 25 June | Completed
|  | 6 | Vendor Booking (Sound, Lights, Decor, etc.) | Manasi | 19 June to 25 June | Completed
|  | 7 | Crew & Volunteer Allocation | Mansi& shreya | 19 June to 25 June | Completed
|  | 8 | Sponsorship Pitch Deck Preparation | Shreya | 19 June to 25 June | Completed
|  | 9 | Sponsor Coordination & Branding | Shreya | 19 June to 25 June | Completed
|  | 10 | Influencer Collaboration Finalized | Shreya | 19 June to 25 June | Completed
|  | 11 | Influencer Content Schedule | Shreya | 19 June to 25 June | Completed
|  | 12 | Material Checklist Preparation | Mansi | 19 June to 25 June | Completed
|  | 13 | Logistics & Transport Planning | Mansi | 19 June to 25 June | Completed
Eco friendly Ganesh Making | Planning & Pre-Production | 1 | Concept Finalization | Rushit | 24 July to 30 July | Completed
|  | 2 | Budget Approval | Rushit | 24 July to 30 July | Completed
|  | 3 | Event Date Finalization | Rushit | 24 July to 30 July | Completed
|  | 4 | Venue Finalization | Rushit | 24 July to 30 July | Completed
|  | 5 | Permission & Licenses (if required) | Rushit | 24 July to 30 July | Completed
|  | 6 | Vendor Booking (Sound, Lights, Decor, etc.) | Rushit | 24 July to 30 July | Completed
|  | 7 | Crew & Volunteer Allocation | Rushit & shreya | 17 July to 23 July | Not Started |  | No Need
|  | 8 | Sponsorship Pitch Deck Preparation | Shreya | 17 July to 23 July | Completed
|  | 9 | Sponsor Coordination & Branding | Shreya | 17 July to 23 July | Completed
|  | 10 | Influencer Collaboration Finalized | Sanya | 17 July to 23 July | Completed
|  | 11 | Influencer Content Schedule | Sanya | 17 July to 23 July | Completed
|  | 12 | Material Checklist Preparation | Rushit | 17 July to 23 July | Completed
|  | 13 | Logistics & Transport Planning | Rushit | 17 July to 23 July | Completed
Fake Sangeet + Techno Night + Garba | Planning & Pre-Production | 1 | Concept Finalization | Rushit & Yash | 2 Sept to 8 Sept | Completed
|  | 2 | Budget Approval | Rushit | 2 Sept to 8 Sept | In Progress
|  | 3 | Event Date Finalization | Rushit & Yash | 2 Sept to 8 Sept | In Progress
|  | 4 | Venue Finalization | Yash | 2 Sept to 8 Sept | Completed
|  | 5 | Permission & Licenses (if required) | Rushit | 2 Sept to 8 Sept | Completed
|  | 6 | Vendor Booking (Sound, Lights, Decor, etc.) | Yash | 9 Sept to 13Sept | In Progress
|  | 7 | Crew & Volunteer Allocation | Rushit & Yash | 9 Sept to 13Sept | Not Started
|  | 8 | Sponsorship Pitch Deck Preparation |  | 2 Sept to 8 Sept | In Progress
|  | 9 | Sponsor Coordination & Branding |  | 2 Sept to 8 Sept | In Progress
|  | 10 | Influencer Collaboration Finalized |  | 2 Sept to 8 Sept | Not Started
|  | 11 | Influencer Content Schedule |  | 2 Sept to 8 Sept | Not Started
|  | 12 | Material Checklist Preparation | Rushit & Yash | 7 Oct to 10 Oct | Not Started
|  | 13 | Logistics & Transport Planning | Rushit & Yash | 7 Oct to 10 Oct | Not Started
Pre-Navratri + Garba Workshop | Planning & Pre-Production | 1 | Concept Finalization | Rushit & Yash | 23 August to 30 Sepmtember | Not Started
|  | 2 | Budget Approval | Rushit | 5 August to 11 August | Not Started
|  | 3 | Event Date Finalization | Rushit & Yash | 5 August to 11 August | Not Started
|  | 4 | Venue Finalization | Yash | 5 August to 11 August | Not Started
|  | 5 | Permission & Licenses (if required) | Rushit | 12 August to 16 August | Not Started
|  | 6 | Vendor Booking (Sound, Lights, Decor, etc.) | Yash | 12 August to 16 August | Not Started
|  | 7 | Crew & Volunteer Allocation | Rushit & Yash | 12 August to 16 August | Not Started
|  | 8 | Sponsorship Pitch Deck Preparation |  | 12 August to 16 August | Not Started
|  | 9 | Sponsor Coordination & Branding |  | 12 August to 16 August | Not Started
|  | 10 | Influencer Collaboration Finalized |  | 12 August to 16 August | Not Started
|  | 11 | Influencer Content Schedule |  | 12 August to 16 August | Not Started
|  | 12 | Material Checklist Preparation | Rushit & Yash | 9 Sept to 12 Sept | Not Started
|  | 13 | Logistics & Transport Planning | Rushit & Yash | 9 Sept to 12 Sept | Not Started
Exclusive Teachers event | Planning & Pre-Production | 1 | Concept Finalization | Vidhi |  | In Progress
|  | 2 | Budget Approval | Vidhi and Ma'am |  | Not Started
|  | 3 | Event Date Finalization | 31st |  | In Progress
|  | 4 | Venue Finalization | Vidhi |  | Not Started
|  | 5 | Permission & Licenses (if required) | Vidhi and sir |  | Not Started
|  | 6 | Vendor Booking (Sound, Lights, Decor, etc.) | Vidhi |  | Not Started
|  | 7 | Crew & Volunteer Allocation | Sanya and Vidhi |  | Not Started
|  | 8 | Sponsorship Pitch Deck Preparation | Vidhi and sir |  | Not Started
|  | 9 | Sponsor Coordination & Branding | Nirav and Sachin |  | Not Started
|  | 10 | Influencer Collaboration Finalized | Sanya |  | Not Started
|  | 11 | Influencer Content Schedule | Sanya |  | Not Started
|  | 12 | Material Checklist Preparation | Vidhi |  | Not Started
|  | 13 | Logistics & Transport Planning | Vidhi and sir |  | Not Started
New Year Party | Planning & Pre-Production | 1 | Concept Finalization | Sir/Mam |  | Completed
|  | 2 | Budget Approval | Mam |  | In Progress
|  | 3 | Event Date Finalization | Mam |  | Completed
|  | 4 | Venue Finalization | Sir/Mam |  | Completed
|  | 5 | Permission & Licenses (if required) | Venue |  | Not Started
|  | 6 | Vendor Booking (Sound, Lights, Decor, etc.) | Venue |  | Not Started
|  | 7 | Crew & Volunteer Allocation | Mam |  | Not Started
|  | 8 | Sponsorship Pitch Deck Preparation | Marketing Team |  | Not Started
|  | 9 | Sponsor Coordination & Branding | Mam/Sir |  | Not Started
|  | 10 | Influencer Collaboration Finalized | Sanya |  | Not Started
|  | 11 | Influencer Content Schedule | Sanya |  | Not Started
|  | 12 | Material Checklist Preparation | Mam |  | Not Started
|  | 13 | Logistics & Transport Planning | Sir |  | Not Started

## Social Media & Ticketing
Event Name | Event Date | Task Phase | Order | Task | Assigned To | Deadline | Status | Details of Post | Ticket Platform Link | Instagram Post Date | Reel Date | Influencer Handles | Linktree Update Done | Platforms | Commission %
Garba Workshop | 26th July 2025 | Social Media & Promotions | 1 | Poster Design | Kashish | 26th June to 2th July | Completed | [6 empty] | All Events | 10%
|  |  | 2 | Venue Logo | Mansi | 19 June to 25 June | Completed | [6 empty] | Book My Show | 10%
|  |  | 3 | Venue Social Media Handles | Mansi | 19 June to 25 June | Completed | [6 empty] | District
|  |  | 4 | Venue Person Name & Designation | Mansi | 19 June to 25 June | Completed | [6 empty] | Wowsly
|  |  | 5 | Venue Person Contact Number | Mansi | 19 June to 25 June | Completed | [6 empty] | Sort my Scene
|  |  | 6 | Ticket Design | Kashish | 26th June to 2th July | Completed | [6 empty] | Showmates
|  |  | 7 | Welcome Board/Sunboard Design | Kashish | 26th June to 2th July | Completed
|  |  | 8 | Script Writing for Event Flow | Mansi/Shreya | 19 June to 25 June | Completed
|  |  | 9 | Reel Shoot Planning | Shreya | 26th June to 2th July | Completed
|  |  | 10 | Influncer Invitation Prepared | Shreya | 26th June to 2th July | Completed
|  |  | 11 | Influncer Invitation Sent | Shreya | 26th June to 2th July | Completed
|  |  | 12 | Influncer Social Media Handles | Shreya | 26th June to 2th July | Completed
|  |  | 13 | Artist Social Media Handles | Mansi | 26th June to 2th July | Completed
|  |  | 14 | Reel Creation & Editing | Kashish | 26th June to 2th July | Completed
|  |  | 15 | Ticket Link Generation (All platforms) | Nikhil/Mansi | 06th July | Completed |  | https://allevents.in/ahmedabad/garba-workshop-26-july-tickets/80002967208581?ref=smdl https://in.bookmyshow.com/events/garba-workshop/ET00454049?webview=true
|  |  | 16 | First Post and Reel Posting | Kashish/Shreya | 06th July | Completed
|  |  | 17 | Last Post and Reel Posting | Kashish/Shreya | 2025-08-02 | Completed
|  |  | 18 | Event Page on Linktree | Nikhil/Shreya | 26th June to 2th July | Completed
|  |  | 19 | Certificates | Kashish | 26th June to 2th July | Completed
|  |  | 20 | Social Media Campaign Plan | Nikhil/Shreya | 26th June to 2th July | Completed
|  |  | 21 | Content Calendar Finalized | Shreya | 26th June to 2th July
|  |  | 22 | Website Post | Shreya | 26th June to 2th July | Completed
|  |  | 23 | Terms & Conditions | Kashish | 26th June to 2th July | Completed
Eco- Friendly Ganesha Workshop | 25th Aug 2025 | Social Media & Promotions | 1 | Poster Design | Kashish | 21th July to 25th July | Completed
|  |  | 2 | Venue Logo | Rushit | 21th July to 25th July | Completed
|  |  | 3 | Venue Social Media Handles | Rushit | 21th July to 25th July | Completed
|  |  | 4 | Venue Person Name & Designation | Rushit | 21th July to 25th July | Completed
|  |  | 5 | Venue Person Contact Number | Rushit | 21th July to 25th July | Completed
|  |  | 6 | Ticket Design | Kashish | 21th July to 25th July
|  |  | 7 | Welcome Board/Sunboard Design | Kashish | 21th July to 25th July | Completed
|  |  | 8 | Script Writing for Event Flow | Rushit/Shreya | 14th July to 20th July | Completed
|  |  | 9 | Reel Shoot Planning | Sanya | 21th July to 25th July | Completed
|  |  | 10 | Influncer Invitation Prepared | Sanya | 21th July to 25th July | Completed
|  |  | 11 | Influncer Invitation Sent | Sanya | 21th July to 25th July | Completed
|  |  | 12 | Influncer Social Media Handles | Sanya | 21th July to 25th July | Completed
|  |  | 13 | Artist Social Media Handles | Rushit | 21th July to 25th July | Completed
|  |  | 14 | Reel Creation & Editing | Kashish | 21th July to 25th July | Completed
|  |  | 15 | Ticket Link Generation (All platforms) | Nikhil/Mansi | 15th August | Completed |  | https://allevents.in/ahmedabad/eco-friendly-ganpati-making-workshop-with-refreshments-and-prasad-tickets/80001776448204?ref=quicksearch-event-results
|  |  | 16 | First Post and Reel Posting | Sanya | 7th August | Completed
|  |  | 17 | Last Post and Reel Posting | Sanya |  | In Progress
|  |  | 18 | Event Page on Linktree | Nikhil/Shreya | 21th July to 25th July | Completed
|  |  | 19 | Certificates | Kashish | 21th July to 25th July | Completed
|  |  | 20 | Social Media Campaign Plan | Nikhil/Shreya | 21th July to 25th July | Completed
|  |  | 21 | Content Calendar Finalized | Shreya | 21th July to 25th July | Completed
|  |  | 22 | Website Post | Shreya | 21th July to 25th July | Completed
|  |  | 23 | Terms & Conditions | Kashish | 21th July to 25th July | Completed

## Sales Activities
Event Name | Tasks | Assigned by | Deadlines | Date | Remarks if any | Other platforms
| Affilate Program | Mansi/Shreya | 27th July |  |  | Swiggy
| Seller Program | mansi/Shreya | 27th July |  |  | Zomato
| Website Sells |  | 27th July |  |  | Blinkit
| All Ticket platforms Sells | mansi | 27th July |  |  | District
All events
[6 empty] | Showmates | Gaming
[6 empty] | Website | 20% less from all other platforms

## Printables
Event Name | Event Date | Printing Materials | Size | Assigned To | Deadlines | Vendor Name | Vendor Contact Number | Printing Material Given Date | Printing Material Received Date
Garba Workshop | 26/07/25 | Posters |  | Mansi | 03/07/25 to 05/07/25
|  | Pamphelts |  | Mansi | 03/07/25 to 05/07/25 | Krishna Poster | 6351611583 | 20/07/25 | 23/07/25
|  | Wall Stickers/Pamplet |  | Mansi | 03/07/25 to 05/07/25
|  | Sunboard/welcome board |  | Mansi | 03/07/25 to 05/07/25 | Krishna Poster | 6351611583 | 20/07/25 | 23/07/25
|  | Standee |  | Mansi | 03/07/25 to 05/07/25 | Krishna Poster | 6351611583 | 20/07/25 | 23/07/25
|  | Brochures |  | Mansi | 03/07/25 to 05/07/25 | Satyam Prints
|  | Flyers |  | Mansi | 03/07/25 to 05/07/25 | Satyam Prints
|  | Press Wall |  | Mansi | 03/07/25 to 05/07/25 | Satyam Prints
|  | Bussiness cards |  | Mansi | 03/07/25 to 05/07/25
|  | Stickers |  | Mansi | 03/07/25 to 05/07/25 | Krishna Poster | 6351611583 | 20/07/25 | 23/07/25
|  | NFC card |  | Mansi | 03/07/25 to 05/07/25 | Cardexia | 7283904329 | 23/07/25
|  | Envolpes |  | Mansi | 03/07/25 to 05/07/25 | Satyam Prints
|  | Thankyou card |  | Mansi | 03/07/25 to 05/07/25 | Satyam Prints
|  | Loyalty card |  | Rushit | 03/07/25 to 05/07/25 | Satyam Prints | 9328810102 | 24/07/25
|  | UE Pass |  | Rushit | 03/07/25 to 05/07/25 | Satyam Prints | 9328810102 | 24/07/25
Eco Friendly Ganpati Making | 25/08/25 | Posters |  | Rushit | 27/07/25 to 29/07/25
|  | Pamphelts |  | Rushit | 27/07/25 to 29/07/25
|  | Wall Stickers |  | Rushit | 27/07/25 to 29/07/25
|  | Sunboard/welcome board |  | Rushit | 27/07/25 to 29/07/25 | Krishna Poster | 6351611583 | 22/08/25 | 23/08/25
|  | Certificate |  | Rushit | 27/07/25 to 29/07/25 | Krishna Poster | 6351611583 | 22/08/25 | 23/08/25
|  | Flash Banner |  | Rushit | 27/07/25 to 29/07/25 | Krishna Poster | 6351611583 | 22/08/25 | 23/08/25
|  | Standee |  | Rushit | 27/07/25 to 29/07/25
|  | Brochures |  | Rushit | 27/07/25 to 29/07/25
|  | Flyers |  | Rushit | 27/07/25 to 29/07/25
|  | Press Wall |  | Rushit | 27/07/25 to 29/07/25
|  | Bussiness cards |  | Rushit | 27/07/25 to 29/07/25
|  | Stickers |  | Rushit | 27/07/25 to 29/07/25
|  | NFC card |  | Rushit | 27/07/25 to 29/07/25
|  | Envolpes |  | Rushit | 27/07/25 to 29/07/25
|  | Thankyou card |  | Rushit | 27/07/25 to 29/07/25
|  | Loyalty card |  | Rushit | 27/07/25 to 29/07/25
|  | UE Pass |  | Rushit | 27/07/25 to 29/07/25
Fake Sangeet + Techno Night + Garba | 13/9/25 | Posters |  | Rushit | 17 AUG to 19 AUG
|  | Pamphelts |  | Rushit | 17 AUG to 19 AUG
|  | Wall Stickers |  | Rushit | 17 AUG to 19 AUG
|  | Sunboard/welcome board |  | Rushit | 17 AUG to 19 AUG
|  | Standee |  | Rushit | 17 AUG to 19 AUG
|  | Brochures |  | Rushit | 17 AUG to 19 AUG
|  | Flyers |  | Rushit | 17 AUG to 19 AUG
|  | Press Wall |  | Rushit | 17 AUG to 19 AUG
|  | Bussiness cards |  | Rushit | 17 AUG to 19 AUG
|  | Stickers |  | Rushit | 17 AUG to 19 AUG
|  | NFC card |  | Rushit | 17 AUG to 19 AUG
|  | Envolpes |  | Rushit | 17 AUG to 19 AUG
|  | Thankyou card |  | Rushit | 17 AUG to 19 AUG
|  | Loyalty card |  | Rushit | 17 AUG to 19 AUG
|  | UE Pass |  | Rushit | 17 AUG to 19 AUG

## Event Day Plan
Event Name | Task Phase | Order | Task | Assigned To | Setup Start Time | Event Start Time | Entry Gates Open | Venue Contact | Crew Assigned | Backup Plan
Garba Workshop | Event Day Execution | 1 | Final Venue Check | Mansi
|  | 2 | Equipment Setup | Mansi/Shreya
|  | 3 | Entry Gates & Security Arrangement | Mansi
|  | 4 | Volunteer Briefing | Mansi/Shreya
|  | 5 | Influencer Management On-site | Shreya
|  | 6 | Photography/Videography Team Coordination | Shreya
|  | 7 | On-Ground Team Briefing | Mansi
|  | 8 | Rehearsal (if applicable) | Mansi/Shreya
|  | 9 | Event Execution & Flow Monitoring | Mansi
Eco friendly Ganesh Making | Event Day Execution | 1 | Final Venue Check | Rushit | 12:50 | 13:00 | 13:00
|  | 2 | Equipment Setup | Rushit | 12:50 | 13:00 | 13:00
|  | 3 | Entry Gates & Security Arrangement | Rushit | 12:50 | 13:00 | 13:00
|  | 4 | Volunteer Briefing | Rushit | NA | 13:00 | 13:00
|  | 5 | Influencer Management On-site | Shreya | 12:50 | 13:00 | 13:00
|  | 6 | Photography/Videography Team Coordination | Shreya | 13:10 | 13:00 | 13:00
|  | 7 | On-Ground Team Briefing | Rushit | 12:50 | 13:00 | 13:00
|  | 8 | Rehearsal (if applicable) | Rushit | 12:50 | 13:00 | 13:00
|  | 9 | Event Execution & Flow Monitoring | Rushit | 13:00 | 13:00 | 13:00
Fake Sangeet + Techno Night + Garba | Event Day Execution | 1 | Final Venue Check | Rushit
|  | 2 | Equipment Setup | Rushit
|  | 3 | Entry Gates & Security Arrangement | Rushit
|  | 4 | Volunteer Briefing | Rushit
|  | 5 | Influencer Management On-site | Shreya
|  | 6 | Photography/Videography Team Coordination | Shreya
|  | 7 | On-Ground Team Briefing | Rushit
|  | 8 | Rehearsal (if applicable) | Rushit
|  | 9 | Event Execution & Flow Monitoring | Rushit

## Post-Event Checklist
Event Name | Task Phase |  | Task | Assisgned to | Deadline | Status | Notes
Garba Workshop | Post Event Activities | 1 | Sharing Raw footages to kashish | Shreya | 26th July Night | Completed
| Post Event Activities | 2 | Post-Event Video Editing & Upload | Kashish | 28th July Morning | Completed
| Post Event Activities | 3 | Tagging Influencers & Sponsors | Shreya/Kashish | 28th July | Completed
| Post Event Activities | 4 | Feedback Collection (Participants + Team) | Shreya/Mansi | 26th July | Completed
| Post Event Activities | 5 | Financial Settlement | Nikita | 27th July | Completed
| Post Event Activities | 6 | Internal Debrief & Learnings | Shreya | 2025-07-27 | Completed
| Post Event Activities | 7 | Social Media Recap Post | Kashish | 28th July | Completed
| Post Event Activities | 8 | Data Entry/Reports Update | Mansi/Shreya | 27th July | Completed
Eco friendly Ganesh Making | Post Event Activities | 1 | Sharing Raw footages to Yash | Sanya | 26 to 27 Aug | In Progress
| Post Event Activities | 2 | Post-Event Video Editing & Upload | Sanya | 26 to 27 Aug | Not Started
| Post Event Activities | 3 | Tagging Influencers & Sponsors | Shreya/Sanya | 26 to 27 Aug | Not Started
| Post Event Activities | 4 | Feedback Collection (Participants + Team) | Shreya/Sanya | 2025-08-24 | Completed
| Post Event Activities | 5 | Financial Settlement | Nikita | 26 to 27 Aug | Not Started
| Post Event Activities | 6 | Internal Debrief & Learnings | Shreya | 26 to 27 Aug | Not Started
| Post Event Activities | 7 | Social Media Recap Post | Sanya | 26 to 27 Aug | Not Started
|  |  | Data Entry/Reports Update | Sanya/Shreya | 2025-08-25 | In Progress
Fake Sangeet + Techno Night + Garba | Post Event Activities | 1 | Sharing Raw footages to kashish | Shreya | 26 to 27 Aug | Not Started
| Post Event Activities | 2 | Post-Event Video Editing & Upload | Kashish | 26 to 27 Aug | Not Started
| Post Event Activities | 3 | Tagging Influencers & Sponsors | Shreya/Kashish | 26 to 27 Aug | Not Started
| Post Event Activities | 4 | Feedback Collection (Participants + Team) | Shreya/Mansi | 26 to 27 Aug | Not Started
| Post Event Activities | 5 | Financial Settlement | Nikita | 26 to 27 Aug | Not Started
| Post Event Activities | 6 | Internal Debrief & Learnings | Shreya | 26 to 27 Aug | Not Started
| Post Event Activities | 7 | Social Media Recap Post | Kashish | 26 to 27 Aug | Not Started
|  |  | Data Entry/Reports Update | Mansi/Shreya | 26 to 27 Aug | Not Started

## 40 days event plan
First 7 days | Event planning, flow making and venue finalization | 2025-11-24
Sponsors
Next 5 days | Preparation of designs- Making | 2025-12-01
social media
Next 3 Days | Printables - send for Printing and make it ready | 2025-12-06 | k
Sales
Next 20 Days | Marketing- Online & Offline | 2025-12-08
Next 4 Days | Pre- event Making & Preps | 28/12
1 Day | Event Day | 2025-12-31
Next 2 days | Post Event Content posting & Financial Settlements